# Public Call for Provision of Technical Assistance to Local Self-Governments in Capital Investment Planning and Programme Budgeting

# ANNEX 3: Tentative Timeline and Activities of the Technical Assistance for Programme Budgeting and Capital Investment Planning Preparation in selected Programme LSGs

The proposed plan of the activities and the timeline are based on the following assumptions:

- The selection process of the LSGs for receiving technical assistance will end in mid-March 2015, so late March could be planned for initiating the process of technical assistance activities;

- The activities and its timetables are planned in accordance with the budget cycle set by the Budget System Law, so the activities of the technical assistance would overlap with the actual budget process in the LSGs. In this way it could be expected that the potential effects of the technical assistance will be instrumental in the LSGs everyday budget practice and that it will create the largest impacts in LSGs.

- The process of PB and CIP preparation will be performed simultaneously; in certain moments those activities will overlap or even performed jointly and in some periods of their implementation they will be performed relatively independent. This is the reason why the dates in the below overview are not always presented chronologically.

| # | Activities | Output | Timeframe |
| --- | --- | --- | --- |
| 1 | Preparatory Work |  |  |
| 1.1 | Introductory meeting with the LSG representatives, development of an initial work plan | Work Plan | Early April – early April 2015 |
| 1.2 | Data collection | Data collected and analysed |  |
| 1.3 | Introductory workshop on PB and CIP | Project beneficiaries prepared to work on CIP and PB |  |
| 2 | Initiating LSG work on PB and CIP |  |  |
| 2.1 | Forming the LSG initiative WG | Work Group | Late April 2015 |
| 2.2 | Preparation and adoption of the decision on initiation of the work on PB and CIP | Adopted Decision |  |
| 2.3 | Preparation and adoption of the procedures/ instructions for PB and CIP preparation including calendar of activities | Procedures and instructions for PB and CIP processes |  |
| 3 | Programme Budget Preparation |  |  |
| 3.1 | Identify LSG potential for PB model implementation | Analysis of each LSG | Late April – early May 2015 |
| 3.2 | Defining the budget programmes/ projects | List of defined programmes/ projects |  |
| 4 | Citizen participation in the process of PB and CIP preparation | Citizens’ input provided |  |
| 4.1 | Develop a plan for citizen participation |  | Late May – early June 2015 |
| 4.2 | Media promotion |  |  |
| 4.3 | Public hearing |  |  |
| 5 | Prioritization of budgetary programmes/ projects, with public contribution and feedback | Defined list of programmes, projects and activities | June 2015 |
| 6 | Creating a Budget Decision | Defined model of budget decision with programme elements | September 2015 |
| 7 | Technical training on CIP preparation | Trained personnel in charge of CIP preparation | March 2015 |
| 8 | Developing policies for capital investment | Formulated ideas of what can and cannot be funded | March 2015 |
| 9 | Establish project ranking and selection criteria and procedure | Rules on how to rank and select projects established | April 2015 |
| 10 | Forming the list of LSG capital projects and capital assets | The list of CIP projects proposed for funding |  |
| 10.1 | Collecting, analysing and processing the information on existing capital projects |  | Late May – early June 2015 |
| 10.2 | Collecting data on LSG capital assets |  |  |
| 10.3 | Collecting proposals for new capital projects and for repair of existing capital assets |  |  |
| 11 | Ranking the projects in accordance with priorities and evaluation model | The list of proposed CIP projects ranked | September 2015 |
| 12 | Preparation of working version of CIP/ financing plan | Prioritization list matched with funding sources | September 2015 |
| 13 | Presentation of the working version of the PB and CIP to the LSG management | PB and CIP presented to the LSG mayor and assembly | October 2015 |
| 14 | Adoption of CIP by LSG assembly | PB and CIP documents adopted by LSG assembly | October 2015 |
| 14 | Adoption of the PB by LSG assembly | PB and CIP documents adopted by LSG assembly | December 2015 |
| 15 | Using PB and CIP as an effective management tool in every day LSG finance and budget practice | LSG finance and budget staff coached in PB and CIP application in everyday practice | 2016 |
| 16 | Capturing lessons learned, summing up if the experiences of the programme LSGs | Summarized experience prepared for dissemination to other LSGs | 2016 |

It should be noted that the proposed dates are tentative and that the Working Groups for CIP could change them in accordance with their other obligations and specifics of their other activities in LSGs. Anyhow, having in mind the budget cycle which is prescribed by the Law on the Budget System and the inter-relations between the PB and CIP preparation process, those changes could not be considerable. The dates which should be considered relatively fixed are the beginning of the process (mid-March 2015) and its end (mid-December 2015).