## Sheet1
Bill of Quantities for stone barrier in cement mortar Location P15 - Community Prokuplje Book 1, Basin Pusta reka up tо the section of the Pusta reka intake into the lake
| DESCRIPTION | Unit | No. of units | Unit price | Total
|  |  |  | (RSD) | (RSD)
IPRELIMINARY WORKS
1 | Cut down softwood trees using motor sow, shorten trunks to a defined length, cut branches and pull trees out to a distance up to 20 meters
1а | ∅ up to 10cm | pcs. | 9
1б | ∅10-30cm | pcs, | 5
2 | Clear the ground of twigs, branches, piled up rubble, as well as sludge, including load-on and transport to a distance of up to 1 km. | m2 | 200
3 | Geodetic marking of structures in the field (barrier). | lump sum. | 1
4 | Construction of access points to deliver the material for the construction of barriers | lump sum. | 1
5 | Temporary land possession. | lump sum. | 1
II EARTH WORKS
6 | Excavate earth for barrier foundation in the ground III and IV by excavating 80% mechanically and 20% manually and load excess earth into lorries.
| Excavation for foundations | m3 | 107
| Excavation for “подслапље”- sub stilling pool and cut-off | m3 | 347
| Calculation per m3 of earth excavated and loaded into lorries | m3 | 454
7 | Build embankment from excavated earth entirely in accordance with relevant regulations and standards. | m3 | 2
Calculation per m3 of embankment.
8 | Transport excess excavated earth to forest roads and spread it evenly using bulldozer, at least three times over for compacting. Average transport distance is about 500 meters. Calculation per m3 of transported, spread and compacted earth. | m3 | 452
9 | Pump water out of the foundation pit or drain water in some other way in order to enable works to proceed. | lump sum. | 1
10 | Construct gravel bedding d=10 cm. Calculation per m3 of bedding installed. | m3 | 12
III STONE WORK
11 | Construct stone barrier in cement mortar. Minimum stone size shall be 25 cm. Payment per m3 of purchased and filled in stone.Payment per m3 of filled in stone. | m3 | 140
12 | Build “podslaplje”- sub stilling pool with stone cut-off in cement mortar. Minimum stone size shall be under 25 cm. Payment per m3 of purchased and filled in stone. | m3 | 91
13 | Build “rizberma”- spillway apron of stone mound, downriver from barrier cut-off, 4 m in length. Payment per m3 of purchased and filled in stone. | m3 | 34
14 | Build beaching from upstream face of barrier. Minimum stone size shall be under 25 cm. Payment per m3 of purchased and filled in stone. | m3 | 36
TOTAL