Infrastructure services (designs)

(Call for proposals)

GRANT SUPPORT METHODOLOGY

PROGRES – GRANTEE

Management Process for services

(Grant initiation, implementation, closing, evaluation)

Method of funds transfer and auditing

- Guidelines for applicants

- Model Grant Contract

- General conditions of contract

- Project Proposal (application form, log frame, budget, reports)

METHOD OF FUNDS TRANSFER AND AUDITING

| No | Description of Task | Task Owner | Timeframe | Responsible |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | European PROGRES |  | GRANTEE |  |
|  | GRANT INITIATION PHASE |  |  |  |  |  |  |
| 1. | The Mayor writes letter of appointment to name responsible counterpart – municipal Grant manager and Project Team (offices for public procurement, legal department and finances, administration and on call experts for preparation of ToR, approval of Concept design and final approval of completion of technical documentation) | Mayor, Grant Manager for technical experts | not latter then 7 after signing the Grant contract |  |  |  |  |
| 2. | Municipality opens separate joint signature Grant project account (opening balance 0,00). Joint account signatories are Mayor and European PROGRES (Infrastructure Sector Manager) - Depositories: European PROGRES and Municipality | Grant Manager, Finance office | not latter then 30 after signing the Grant contract |  |  |  |  |
| 3. | Municipality fills in Vendor Form with account detail and sends it to European PROGRES | Grant Manager, Finance office | not latter then 7 after project account opening |  |  |  |  |
| 4. | Municipality submits the list of authorized person/s to sign the tax exemption forms with central Tax Office - SPECIMEN | Mayor, Grant Manager and Finance office | not latter then 7 after signing the Grant contract |  |  |  |  |
|  | GRANT IMPLEMENTATION PHASE |  |  |  |  |  |  |
| 1. | Municipality transfers entire co-funding on the project account | Mayor, Grant Manager and Finance office | not latter then 30 after signing the Grant contract |  |  |  |  |
| 2. | Municipality prepares request for transferring European PROGRES funds according to payment schedule specified in the Grant Contract | Grant Manager and Finance office | after transfer of co-funding |  |  |  |  |
| 3. | European PROGRES transfers the VAT exempted funds into the grant project account, respecting the payment schedule from the Grant Contract | European PROGRES Engineer and finance department | not latter then 30 after receiving the request |  |  |  |  |
| 4. | Implementation of project activities – procurement, designing, technical control. This process is specified in details in the separate section below. | Grant Manager | duration of the Grant agreement |  |  |  |  |
| 5. | The municipal account signatory and European PROGRES signatory sign jointly transfer of funds to the contractors – payment certificates must be approved by technical experts and programme engineer | Grant Manager, Finance department, technical experts and European PROGRES engineer | duration of the Grant agreement |  |  |  |  |
| 6. | The Grantee keeps the project financial record – project budget, project financial breakdown sheet, planned against achieved record (templates attached) | Grant Manager, Finance department, European PROGRES engineer | duration of the Grant agreement |  |  |  |  |
| 7. | The grantee sends interim narrative and financial reports as per contract agreement. (Template report forms attached) | Grant Manager, Finance department | according to the dynamic defined in the Grant contract |  |  |  |  |
| 8. | European PROGRES performs interim budget audit, before every payment | European PROGRES audit department | before every payment |  |  |  |  |
|  | PROJECT CLOSING PHASE |  |  |  |  |  |  |
| 1. | After all project activities are completed Grantee submits final narrative and financial reports, final budget. All services must be certified as completed before submitting the reports | Grant Manager, Project team, European PROGRES engineer | Upon finishing of all project activities |  |  |  |  |
| 2. | European PROGRES proceeds with final audit, as per general conditions of contract | European PROGRES audit department | Upon submission of the final reports |  |  |  |  |

| Implementation of project activities – procurement and designing |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| No | Description of Task | Task Owner | Timeframe | Responsible |  |  |
|  |  |  |  | European PROGRES | GRANTEE |  |
| 1. | Preparation of decision for starting the public procurement, appointing of commission, preparation of public procurement plan, establishment of Project team that includes Technical expert; preparation of the Action Plan | Mayor, Grant Manager, public procurement commission | 7 after signing the Grant contract |  |  |  |
| 2. | Preparation of designing task that will be included in the public procurement package | Grant Manager, Technical experts of the Project team | 7 after appointment |  |  |  |
| 3. | Preparation of tender package in consultation with Technical experts from the Project team | Grant manager, public procurement commission | 14 after appointment |  |  |  |
| 4. | Approval of the public procurement package before advertisement | European PROGRES | 7days upon submission |  |  |  |
| 5. | Conducting of the Public procurement process for designing | Grant manager, public procurement commission |  |  |  |  |
| 6. | Conducting of the Public procurement process for the technical control | Grant manager, public procurement commission |  |  |  |  |
| 7. | Approval of the public procurement procedure before contract signing | European PROGRES | 7days upon submission |  |  |  |
| 8. | Contract signing with selected designing company | Grant Manager, Mayor, Designing company |  |  |  |  |
| 9. | Contract signing with selected company for technical control | Grant Manager, Mayor, company for technical control |  |  |  |  |
| 10. | Preparation and presentation of the concept design to the Project team | designing company, Grant Manager, Technical experts |  |  |  |  |
| 11. | Analyses and approval of concept design submitted and presented by the designing company | Grant Manager, Technical experts, company for technical control and European PROGRES engineer |  |  |  |  |
| 12. | Development of the full set of technical documentation as per Concept design approved by Technical experts | Grant Manager, designing company, company for technical control |  |  |  |  |
| 13. | Technical control of the technical documentation | Grant Manager, company for technical control, designing company, |  |  |  |  |
| 14. | Approval of content and preparation of the Report on completion of the submitted technical documentation | Grant Manager, technical experts and European PROGRES engineer |  |  |  |  |